## Project Tracker
Task Name | Status | Notes | Risk Flag | Due Date | Owner | Workstream | Milestone
Project kickoff completed | Complete | Kickoff meeting held and materials distributed |  | 2026-01-10 | Mark | Initiation | Yes
Requirements gathering | In Progress | Stakeholder interviews ongoing |  | 2026-01-20 | Alex | Planning
Architecture design | In Progress | Initial draft created, pending security review |  | 2026-01-25 | Jamie | Design
Security review | Blocked | Waiting on external security team approval | Yes | 2026-01-18 | Vendor | Security
API development | In Progress | Core endpoints under development |  | 2026-02-05 | Chris | Development
Frontend prototype | Complete | Initial UI prototype approved |  | 2026-01-15 | Taylor | Development
Integration testing | Not Started | Dependent on API completion |  | 2026-02-10 | QA Team | Testing
Data migration | At Risk | Legacy data inconsistencies identified | Yes | 2026-02-01 | Ops | Migration
UAT planning | In Progress | Test cases being drafted |  | 2026-01-30 | QA Team | Testing
Go-Live readiness | Pending | Awaiting completion of testing activities |  | 2026-02-15 | PMO | Deployment | Yes